## V4 SQA Report
Robotics Programming Lab - v4 SQA Verification Report
Release | v4 Classroom Security Candidate | Branch | staging main | Test Date | 2026-08-04
Commit | Initial staging candidate; SHA recorded in Git/GitHub | Frontend | https://robotics-programming-lab.vercel.app/ | Backend | https://robotics-programming-lab-api.onrender.com
Scope | Verified local staging workflow plus classroom-security implementation. Private staging repository created; production repository remains unchanged. Hosted staging CI and live sandbox deployment remain open.
Total Checks | 46 | Passed | 36 | Non-Pass / Open | 10
Pass Rate | 78.26% | Blocked | 0 | Not Run / Deferred | 5
Decision | CLASSROOM CANDIDATE - LIVE GATES OPEN
Check ID | Area / Feature | Result | Environment | Evidence | Limitation / Next Step
V4-SQA-001 | Source and tracked-secret audit | Pass | Local repository | Clean tracked source; venv ignored; one synthetic migration URL scanner match. | No real credential detected in tracked files.
V4-SQA-002 | Backend automated tests | Pass | Local | 76 pytest checks passed in 27.38 seconds. | Includes auth, assignment, grader, migration, rate-limit, remote-sandbox, and sandbox-service tests.
V4-SQA-003 | Python dependency integrity | Pass | Local | pip check: no broken requirements. | Fresh Python 3.11 venv created from backend requirements.
V4-SQA-004 | Python compilation | Pass | Local | compileall completed without error. | Backend modules compile.
V4-SQA-005 | Flutter static analysis | Pass | Local | flutter analyze: no issues found. | Current v4 source.
V4-SQA-006 | Flutter automated tests | Pass | Local | 33 tests passed. | Includes login entry, session policy, responsive UI, progress, execution state, and secure-grader loading.
V4-SQA-007 | Flutter release web build | Pass | Local | Production web build completed in .flutter_build/web. | Built with the live Render API URL.
V4-SQA-008 | Hosted CI and deployment | Pass | GitHub/Vercel | Latest v4 verification and Vercel deployment succeeded. | Existing hosted baseline passed; new classroom-security working tree is not yet pushed or deployed.
V4-SQA-009 | Live health and exact-origin CORS | Pass | Render | Health API 4.0.0; exact Vercel origin allowed. | Live API checks passed.
V4-SQA-010 | Login-first shared URL | Pass | Live Chrome | Public root displayed login despite prior saved session. | Demo credentials were not shown on the page.
V4-SQA-011 | Invalid login handling | Pass | Live Chrome/API | Invalid credential returned a clear error and remained on login. | No endless spinner or crash.
V4-SQA-012 | Student authentication/session/logout | Pass | Live Chrome/API | Student login, /app session, auth/me, and token revocation passed. | Anonymous assignment access returned 401.
V4-SQA-013 | Student catalog and navigation | Pass | Live Chrome | Exactly four assignment cards loaded in order. | Assignment 1 opened successfully.
V4-SQA-014 | Assignment workspace and image | Pass | Live Chrome/API | Starter code, instructions, scenario image, and results panel loaded. | Image endpoint returned image/png.
V4-SQA-015 | Run tests completion | Pass | Live Chrome/API | Starter run returned structured evidence and UI stopped running. | Expected starter score was 0%; this is not a product failure.
V4-SQA-016 | AI default and no-AI path | Pass | Live Chrome/API | AI toggle was off and no-AI run completed. | OpenAI provider behavior intentionally not exercised.
V4-SQA-017 | Instructor login and assignment studio | Pass | Live Chrome/API | Instructor role loaded four published assignments and management controls. | Role-protected admin API passed.
V4-SQA-018 | Instructor student-account view | Pass | Live Chrome/API | One active demo student loaded; create/manage controls rendered. | No production account mutation performed.
V4-SQA-019 | Hidden grader and solution protection | Pass | Automated/live API | Student responses excluded hidden_tests, official_solution, and reference_solution. | Ownership and authorization tests passed.
V4-SQA-020 | Official solutions for assignments 1-4 | Pass | Automated | All four official solutions passed modular graders. | Assignment versions 3, 2, 3, and 2 verified.
V4-SQA-021 | Neon persistence | Partial | Live backend | Live PostgreSQL-backed auth, assignments, submission, and admin reads succeeded. | A restart/restore persistence drill was not performed in this run.
V4-SQA-022 | Responsive and accessibility coverage | Partial | Automated/live Chrome | Responsive widget and narrow-result tests passed; desktop Chrome passed. | Independent mobile-device, keyboard, text-scale, and accessibility audit remain.
V4-SQA-023 | AI provider-on behavior | Deferred | Live backend | Not run by project decision. | Validate later with quota, timeout, injection, and hidden-data tests.
V4-SQA-024 | Password reset and email | N/A | Professor demo | Feature intentionally disabled for v4 professor demo. | Instructor-managed credentials remain available.
V4-SQA-025 | Destructive instructor mutations | Not Run | Live production | Create/edit/publish/archive/student mutation not performed against production data. | Equivalent maintained backend tests passed.
V4-SQA-026 | Dedicated sandbox service implementation | Partial | Local architecture/smoke | Separate authenticated execution service passed local contract and two-process smoke; it receives no database/OpenAI secrets. | Render Docker image and live sandbox deployment are not yet verified.
V4-SQA-027 | Restart, backup, restore, and rollback drill | Not Run | Hosting operations | No provider restart or database restore drill performed. | Complete before a formal study release.
V4-SQA-028 | Overall classroom release assessment | Partial | Combined | Local classroom-security implementation and retained live professor-demo paths pass. | Do not distribute to students until the sandbox image, live deployment, persistence restart, and restore gates pass.
V4-SQA-029 | Remote sandbox client and service contract | Pass | Local automated | Authenticated requests, response validation, capacity controls, unsafe API rejection, and safe failures passed. | Covered by the 76-test backend suite.
V4-SQA-030 | Separate-process secure grading smoke | Pass | Local API + sandbox services | Both health checks passed; four assignments loaded; Assignment 2 passed through remote grading; import os was rejected. | Processes were stopped after the smoke test.
V4-SQA-031 | Sandbox secret exclusion | Pass | Local security test | OPENAI_API_KEY, DATABASE_URL, and SANDBOX_API_TOKEN were absent from the student worker environment. | The sandbox service itself has no database or OpenAI environment variables.
V4-SQA-032 | Production isolation configuration | Pass | Local configuration | Production rejects subprocess mode and incomplete remote configuration; Render YAML parses two services. | Render Blueprint sync and image build remain unverified.
V4-SQA-033 | Password hashing and account lifecycle | Pass | Local automated | Instructor-created password is stored only as a recommended Argon2 hash; deactivation revokes sessions and preserves records. | Instructor manages unique student IDs and shared credentials.
V4-SQA-034 | Cross-student submission isolation | Pass | Local automated | A second student received 404/403 for another student's hint and solution requests. | Submission owner identity is derived from the authenticated session.
V4-SQA-035 | Execution quota bypass protection | Pass | Local automated | Execution quotas follow the authenticated account; changing X-Forwarded-For does not bypass the limit. | Single-instance in-memory limiter is acceptable for the free classroom deployment; reassess before scaling.
V4-SQA-036 | Secure grader bounded UI | Pass | Local Flutter | Execution waits at most 90 seconds, explains free-tier wake-up, stops on error, and permits retry; analyzer and 33 tests pass. | The first free-tier run may still take about one minute.
V4-SQA-037 | Sandbox image and live deployment | Not Run | Docker / Render | Docker CLI is unavailable locally and the new sandbox service has not been deployed. | Build on Render or Docker CI, set SANDBOX_URL, then repeat live correct/unsafe/restart checks before students use the URL.
V4-SQA-038 | Occupied-port collision protection | Pass | Local PowerShell | Default launch refused existing v3 listeners on ports 5000 and 8080 and identified the owning PIDs. | The launcher cannot silently attach to an older backend or frontend.
V4-SQA-039 | One-command local service orchestration | Pass | Local PowerShell | run-local.ps1 started dedicated sandbox, API, and OneDrive-safe Flutter web on isolated ports. | AI is off by default and the local staging database is isolated.
V4-SQA-040 | Local authentication and catalog smoke | Pass | Local API smoke | Demo student login returned 200 and the authenticated catalog returned all four assignments. | Credentials remain absent from the login page.
V4-SQA-041 | Local execution boundary smoke | Pass | Local API/sandbox | API reported sandbox=remote; sandbox reported dedicated-service; import os failed with structured evidence. | The smoke used the same separate-process contract planned for production.
V4-SQA-042 | Managed local cleanup | Pass | Local PowerShell | stop-local.ps1 stopped frontend, sandbox, and backend process trees; zero managed listeners remained. | Only PIDs recorded by the staging launcher are targeted.
V4-SQA-043 | Complete local release gate | Pass | Local automated | 76 backend tests, pip check, compileall, Flutter analyzer, 33 Flutter tests, and release web build passed. | Release build used the production API URL define in a clean LocalAppData copy.
V4-SQA-044 | Separate private staging repository | Pass | GitHub/local Git | CS-Ponkoj/Robotics-Programming-Lab-Staging was created private; origin points to staging and production points to the live repository. | The retired IUSE repository remains archive-only.
V4-SQA-045 | Exact-commit production promotion guard | Pass | Local source review | Promotion script requires clean staging main, matching origin SHA, fast-forward ancestry, fresh release tag, full SQA, and an atomic push. | The script has not been executed; production is unchanged.
V4-SQA-046 | Hosted staging CI | Not Run | GitHub Actions | CI now includes repository safety, PostgreSQL migration, backend, Flutter, and sandbox Docker image smoke jobs. | Run and verify after the initial staging main push.

## Release Dashboard
Robotics Programming Lab - SQA Release Dashboard
Complete the Master Checklist for every release. Attach evidence, link defects, retest fixes, and obtain sign-off before publishing.
Release / Version | v4 Classroom Security Candidate | Branch | v4-live | Commit | Working tree - not committed | Test Date | 2026-08-04
SQA Owner | Codex SQA | Environment | Local security + retained live baseline | Backend URL | https://robotics-programming-lab-api.onrender.com | Frontend Target | Chrome / Flutter Web
Scope Notes | Dedicated sandbox implementation passes locally. Live sandbox image/deploy, Neon restart/restore, destructive production mutations, independent accessibility, and AI-on remain open.
Release Readiness
Metric | Value | Metric | Value | Metric | Value | Metric | Value
Total Checks | 203 | Current Scope | 191 | Passed | 134 | Failed | 0
Blocked | 0 | Not Run | 46 | Deferred | 14 | N/A | 5
Completion | 72.77% | Pass Rate | 100% | Release Gate Fail/Blocked | 0 | Decision | TESTING INCOMPLETE
Category Coverage
Category | Total | Pass | Fail | Blocked | Not Run | N/A | Progress
Environment & Startup | 11 | 8 | 0 | 0 | 3 | 0 | 72.73%
Health & Public API | 11 | 9 | 0 | 0 | 1 | 1 | 90.91%
Student Catalog & Navigation | 10 | 10 | 0 | 0 | 0 | 0 | 100%
Assignment Workspace & Editor | 16 | 11 | 0 | 0 | 5 | 0 | 68.75%
Grading & Execution | 18 | 18 | 0 | 0 | 0 | 0 | 100%
Sandbox, Security & Privacy | 15 | 8 | 0 | 0 | 3 | 0 | 53.33%
Feedback & Tutoring | 13 | 9 | 0 | 0 | 2 | 0 | 69.23%
Solutions & Learning Progress | 12 | 8 | 0 | 0 | 4 | 0 | 66.67%
Instructor Assignment Studio | 17 | 8 | 0 | 0 | 9 | 0 | 47.06%
Authentication & Account Management | 22 | 18 | 0 | 0 | 1 | 3 | 95.45%
Assignment Content & Pedagogy | 10 | 6 | 0 | 0 | 4 | 0 | 60%
Responsive, Accessibility & Usability | 10 | 6 | 0 | 0 | 4 | 0 | 60%
Data, Infrastructure & Deployment | 14 | 5 | 0 | 0 | 8 | 1 | 42.86%
Automated Quality & Release | 12 | 10 | 0 | 0 | 2 | 0 | 83.33%
Open product/architecture plan

## Master Checklist
Checked? | Check ID | Scope | Category | Feature / Requirement | Preconditions | Test Steps | Expected Result | Priority | Test Type | Platform | Automated? | Status | Defect ID | Actual Result / Evidence | Tester | Test Date | Retest Status | Notes
[x] | ENV-001 | Current | Environment & Startup | Repository clone contains required source and configuration files | Application dependencies are installed and the target environment is available. | Clone the repository; verify backend, frontend, assignments, course_materials, Dockerfiles, Compose, README, and plan artifacts are present. | Required project structure is complete and no required imported source file is missing. | Release Gate | Inspection | Repository | Partial | Pass |  | Fresh v4 local setup/install plus Flutter analyzer, 33 tests, and release web build passed on 2026-08-04. | Codex SQA | 2026-08-04 | Not Required
[x] | ENV-002 | Current | Environment & Startup | Secrets are not committed | Application dependencies are installed and the target environment is available. | Run Git secret and tracked-file checks; inspect .gitignore and tracked files for .env, API keys, admin tokens, databases, and credentials. | No secret, backend/.env, database, or credential value is tracked. | Release Gate | Security | Repository | Partial | Pass |  | Fresh v4 local setup/install plus Flutter analyzer, 33 tests, and release web build passed on 2026-08-04. | Codex SQA | 2026-08-04 | Not Required
[x] | ENV-003 | Current | Environment & Startup | Python virtual environment can be created | Application dependencies are installed and the target environment is available. | Run python -m venv venv in a clean checkout. | Virtual environment is created without errors. | P1 | Installation | Windows | No | Pass |  | Fresh v4 local setup/install plus Flutter analyzer, 33 tests, and release web build passed on 2026-08-04. | Codex SQA | 2026-08-04 | Not Required
[x] | ENV-004 | Current | Environment & Startup | Backend dependencies install | Application dependencies are installed and the target environment is available. | Run .\venv\Scripts\python.exe -m pip install -r .\backend\requirements.txt. | All required packages install successfully. | Release Gate | Installation | Windows | No | Pass |  | Fresh v4 local setup/install plus Flutter analyzer, 33 tests, and release web build passed on 2026-08-04. | Codex SQA | 2026-08-04 | Not Required
[x] | ENV-005 | Current | Environment & Startup | Python dependency integrity | Application dependencies are installed and the target environment is available. | Run .\venv\Scripts\python.exe -m pip check. | Command reports no broken requirements. | Release Gate | Automated | Backend | Yes | Pass |  | Fresh v4 local setup/install plus Flutter analyzer, 33 tests, and release web build passed on 2026-08-04. | Codex SQA | 2026-08-04 | Not Required
[x] | ENV-006 | Current | Environment & Startup | Flutter dependencies resolve | Application dependencies are installed and the target environment is available. | From frontend run flutter pub get. | Flutter resolves dependencies without errors. | Release Gate | Installation | Flutter | No | Pass |  | Fresh v4 local setup/install plus Flutter analyzer, 33 tests, and release web build passed on 2026-08-04. | Codex SQA | 2026-08-04 | Not Required
[ ] | ENV-007 | Current | Environment & Startup | Backend starts locally | Application dependencies are installed and the target environment is available. | Run .\venv\Scripts\python.exe .\backend\run.py and observe startup. | FastAPI starts on the configured host/port and remains stable. | Release Gate | Smoke | Backend | No | Not Run |  |  |  |  | Not Required
[ ] | ENV-008 | Current | Environment & Startup | Frontend starts in Chrome | Application dependencies are installed and the target environment is available. | Keep backend running; from frontend run flutter run -d chrome --dart-define=API_BASE_URL=http://127.0.0.1:5000. | Chrome opens the application and the catalog loads. | Release Gate | Smoke | Web | No | Not Run |  |  |  |  | Not Required
[x] | ENV-009 | Current | Environment & Startup | OneDrive-safe Flutter build output | Application dependencies are installed and the target environment is available. | Build or run from the OneDrive checkout using the configured .flutter_build path. | Flutter creates assets without directory deletion or shader write failures. | P1 | Regression | Windows/Web | Partial | Pass |  | Fresh v4 local setup/install plus Flutter analyzer, 33 tests, and release web build passed on 2026-08-04. | Codex SQA | 2026-08-04 | Not Required
[x] | ENV-010 | Current | Environment & Startup | Backend URL is configurable | Application dependencies are installed and the target environment is available. | Build/run with a nondefault API_BASE_URL and inspect requests. | Frontend sends requests to the supplied URL, including image URLs and Monaco configuration. | P1 | Configuration | Flutter | Partial | Pass |  | Fresh v4 local setup/install plus Flutter analyzer, 33 tests, and release web build passed on 2026-08-04. | Codex SQA | 2026-08-04 | Not Required
[ ] | ENV-011 | Current | Environment & Startup | Backend environment file loads | Application dependencies are installed and the target environment is available. | Place nonsecret test configuration in backend/.env; restart backend; inspect /health and relevant behavior. | Settings load from backend/.env while the file remains ignored. | P1 | Configuration | Backend | Partial | Not Run |  |  |  |  | Not Required
[x] | API-001 | Current | Health & Public API | Health endpoint responds | Application dependencies are installed and the target environment is available. | GET /health. | HTTP 200 returns status ok, API version, database type, and sandbox type. | Release Gate | API | Backend | Yes | Pass |  | 76 backend tests passed; live API health/auth/CORS/assignment/image checks passed 13/13. | Codex SQA | 2026-08-04 | Not Required
[x] | API-002 | Current | Health & Public API | OpenAPI documentation loads | Application dependencies are installed and the target environment is available. | Open /docs. | Interactive FastAPI documentation loads and lists supported public/admin endpoints. | P1 | API | Backend | No | N/A |  | Intentionally disabled or unnecessary for the controlled v4 professor demo. | Codex SQA | 2026-08-04 | Not Required | Preserved for a future broader study release where applicable.
[x] | API-003 | Current | Health & Public API | Assignment list endpoint | Application dependencies are installed and the target environment is available. | GET /assignments and GET /assignments/. | HTTP 200 returns four published assignments in numeric order. | Release Gate | API | Backend | Yes | Pass |  | 76 backend tests passed; live API health/auth/CORS/assignment/image checks passed 13/13. | Codex SQA | 2026-08-04 | Not Required
[x] | API-004 | Current | Health & Public API | Assignment detail endpoint | Application dependencies are installed and the target environment is available. | GET /assignments/{id} for IDs 1 through 4. | Each response contains student-visible assignment data and correct stable ID/version. | Release Gate | API | Backend | Yes | Pass |  | 76 backend tests passed; live API health/auth/CORS/assignment/image checks passed 13/13. | Codex SQA | 2026-08-04 | Not Required
[x] | API-005 | Current | Health & Public API | Unknown assignment returns JSON 404 | Application dependencies are installed and the target environment is available. | GET /assignments/999. | HTTP 404 returns the documented JSON error. | P1 | Negative API | Backend | Yes | Pass |  | 76 backend tests passed; live API health/auth/CORS/assignment/image checks passed 13/13. | Codex SQA | 2026-08-04 | Not Required
[x] | API-006 | Current | Health & Public API | Assignment image endpoint | Application dependencies are installed and the target environment is available. | GET /images/1 and inspect content type/signature. | HTTP 200 returns the expected PNG image. | P1 | API | Backend | Yes | Pass |  | 76 backend tests passed; live API health/auth/CORS/assignment/image checks passed 13/13. | Codex SQA | 2026-08-04 | Not Required
[x] | API-007 | Current | Health & Public API | Unknown image returns JSON 404 | Application dependencies are installed and the target environment is available. | GET /images/999. | HTTP 404 returns the documented JSON error. | P2 | Negative API | Backend | Yes | Pass |  | 76 backend tests passed; live API health/auth/CORS/assignment/image checks passed 13/13. | Codex SQA | 2026-08-04 | Not Required
[x] | API-008 | Current | Health & Public API | Legacy grading compatibility | Application dependencies are installed and the target environment is available. | POST valid code to /grade/{id}. | Legacy route returns the current structured grading contract. | P1 | Compatibility | Backend | Yes | Pass |  | 76 backend tests passed; live API health/auth/CORS/assignment/image checks passed 13/13. | Codex SQA | 2026-08-04 | Not Required
[x] | API-009 | Current | Health & Public API | CORS permits configured frontend | Application dependencies are installed and the target environment is available. | Run frontend from the allowed origin and call public endpoints. | Browser requests succeed without CORS errors; unapproved origins follow configured policy. | P1 | Integration | Web/Backend | Partial | Pass |  | 76 backend tests passed; live API health/auth/CORS/assignment/image checks passed 13/13. | Codex SQA | 2026-08-04 | Not Required
[x] | API-010 | Current | Health & Public API | Malformed JSON is rejected | Application dependencies are installed and the target environment is available. | POST malformed JSON to a submission endpoint. | Request returns controlled HTTP 400 without server crash or stack-trace leakage. | P1 | Negative API | Backend | Yes | Pass |  | 76 backend tests passed; live API health/auth/CORS/assignment/image checks passed 13/13. | Codex SQA | 2026-08-04 | Not Required
[ ] | API-011 | Current | Health & Public API | Request timeout behavior is bounded | Application dependencies are installed and the target environment is available. | Simulate an unavailable or nonresponsive backend. | Frontend leaves loading state within configured timeout and shows a recovery action. | P1 | Resilience | Flutter | Partial | Not Run |  |  |  |  | Not Required
[x] | CAT-001 | Current | Student Catalog & Navigation | Catalog header and identity | Application dependencies are installed and the target environment is available. | Open the landing page. | Robotics Programming Lab identity and subtitle render correctly. | P2 | UI | Web/Mobile | Yes | Pass |  | 32 Flutter tests passed; live Chrome student catalog showed four ordered assignments. | Codex SQA | 2026-08-04 | Not Required
[x] | CAT-002 | Current | Student Catalog & Navigation | Four assignment cards render | Application dependencies are installed and the target environment is available. | Load the catalog. | Exactly four current published assignment cards render with title, number, description, and action. | Release Gate | UI/API | Web/Mobile | Partial | Pass |  | 32 Flutter tests passed; live Chrome student catalog showed four ordered assignments. | Codex SQA | 2026-08-04 | Not Required
[x] | CAT-003 | Current | Student Catalog & Navigation | Assignment ordering | Application dependencies are installed and the target environment is available. | Inspect catalog order. | Assignments are ordered 1, 2, 3, 4. | P1 | UI | Web/Mobile | Yes | Pass |  | 32 Flutter tests passed; live Chrome student catalog showed four ordered assignments. | Codex SQA | 2026-08-04 | Not Required
[x] | CAT-004 | Current | Student Catalog & Navigation | Progress summary default | Application dependencies are installed and the target environment is available. | Open with cleared local progress. | Summary shows 0 of 4 completed and 0 percent. | P1 | State | Web/Mobile | Yes | Pass |  | 32 Flutter tests passed; live Chrome student catalog showed four ordered assignments. | Codex SQA | 2026-08-04 | Not Required
[x] | CAT-005 | Current | Student Catalog & Navigation | Progress badges | Application dependencies are installed and the target environment is available. | Record attempts, completion, and solution reveal; return to catalog. | Cards distinguish Not started, Attempted, Completed, last score, and Solution viewed states. | P1 | State | Web/Mobile | Yes | Pass |  | 32 Flutter tests passed; live Chrome student catalog showed four ordered assignments. | Codex SQA | 2026-08-04 | Not Required
[x] | CAT-006 | Current | Student Catalog & Navigation | Open assignment | Application dependencies are installed and the target environment is available. | Select Start assignment on each card. | Correct assignment workspace opens without losing assignment identity. | Release Gate | Navigation | Web/Mobile | Partial | Pass |  | 32 Flutter tests passed; live Chrome student catalog showed four ordered assignments. | Codex SQA | 2026-08-04 | Not Required
[x] | CAT-007 | Current | Student Catalog & Navigation | Return to catalog | Application dependencies are installed and the target environment is available. | Open an assignment and use Home/back navigation. | Catalog returns and refreshed progress is visible. | P1 | Navigation | Web/Mobile | Yes | Pass |  | 32 Flutter tests passed; live Chrome student catalog showed four ordered assignments. | Codex SQA | 2026-08-04 | Not Required
[x] | CAT-008 | Current | Student Catalog & Navigation | Catalog loading state | Application dependencies are installed and the target environment is available. | Throttle assignment-list response. | Skeleton/loading state renders without layout breakage. | P2 | UI/Resilience | Web/Mobile | Yes | Pass |  | 32 Flutter tests passed; live Chrome student catalog showed four ordered assignments. | Codex SQA | 2026-08-04 | Not Required
[x] | CAT-009 | Current | Student Catalog & Navigation | Catalog error and retry | Application dependencies are installed and the target environment is available. | Stop backend, load catalog, restart backend, select retry. | Actionable error appears and retry reloads assignments successfully. | P1 | Resilience | Web/Mobile | Yes | Pass |  | 32 Flutter tests passed; live Chrome student catalog showed four ordered assignments. | Codex SQA | 2026-08-04 | Not Required
[x] | CAT-010 | Current | Student Catalog & Navigation | Instructor entry point | Application dependencies are installed and the target environment is available. | Select the instructor shield icon. | Instructor assignment studio opens; student progress remains unaffected. | P1 | Navigation | Web/Mobile | Partial | Pass |  | 32 Flutter tests passed; live Chrome student catalog showed four ordered assignments. | Codex SQA | 2026-08-04 | Not Required
[x] | WRK-001 | Current | Assignment Workspace & Editor | Correct assignment header | Application dependencies are installed and the target environment is available. | Open every assignment. | Header shows assignment number, title, progress state, Home action, and AI toggle. | P1 | UI | Web/Mobile | Partial | Pass |  | Flutter tests passed; live Assignment 1 workspace, starter code, instructions, image, and results rendered. | Codex SQA | 2026-08-04 | Not Required
[x] | WRK-002 | Current | Assignment Workspace & Editor | Starter code loads | Application dependencies are installed and the target environment is available. | Open a fresh assignment with no saved draft. | Version-correct starter code populates the editor. | Release Gate | Integration | Web/Mobile | Partial | Pass |  | Flutter tests passed; live Assignment 1 workspace, starter code, instructions, image, and results rendered. | Codex SQA | 2026-08-04 | Not Required
[x] | WRK-003 | Current | Assignment Workspace & Editor | Starter code is syntactically executable | Application dependencies are installed and the target environment is available. | Compile and submit starter code for assignments 1 through 4. | Each starter runs without unintended SyntaxError or IndentationError. | Release Gate | Regression | Backend | Yes | Pass |  | Flutter tests passed; live Assignment 1 workspace, starter code, instructions, image, and results rendered. | Codex SQA | 2026-08-04 | Not Required
[ ] | WRK-004 | Current | Assignment Workspace & Editor | Code editing | Application dependencies are installed and the target environment is available. | Type, delete, paste, and indent Python code. | Editor accurately reflects edits and retains Python formatting. | P1 | UI | Web | No | Not Run |  |  |  |  | Not Required
[x] | WRK-005 | Current | Assignment Workspace & Editor | Keyboard test execution | Application dependencies are installed and the target environment is available. | Press Ctrl+Enter while the editor is active. | Exactly one test run starts. | P1 | Keyboard | Web/Desktop | Yes | Pass |  | Flutter tests passed; live Assignment 1 workspace, starter code, instructions, image, and results rendered. | Codex SQA | 2026-08-04 | Not Required
[x] | WRK-006 | Current | Assignment Workspace & Editor | Run button execution | Application dependencies are installed and the target environment is available. | Select Run tests. | Button enters running state, blocks duplicate execution, then returns to enabled state. | Release Gate | UI/Integration | Web/Mobile | Yes | Pass |  | Flutter tests passed; live Assignment 1 workspace, starter code, instructions, image, and results rendered. | Codex SQA | 2026-08-04 | Not Required
[ ] | WRK-007 | Current | Assignment Workspace & Editor | Draft autosave | Application dependencies are installed and the target environment is available. | Edit code; wait for debounce; leave assignment. | Draft is persisted for the assignment. | P1 | State | Web/Mobile | Partial | Not Run |  |  |  |  | Not Required
[x] | WRK-008 | Current | Assignment Workspace & Editor | Draft restore | Application dependencies are installed and the target environment is available. | Reopen an assignment after saving a draft. | Saved draft replaces starter code only for that assignment. | P1 | State | Web/Mobile | Yes | Pass |  | Flutter tests passed; live Assignment 1 workspace, starter code, instructions, image, and results rendered. | Codex SQA | 2026-08-04 | Not Required
[x] | WRK-009 | Current | Assignment Workspace & Editor | Independent assignment drafts | Application dependencies are installed and the target environment is available. | Save different code in two assignments and reopen both. | Each assignment restores only its own draft. | P1 | State | Web/Mobile | Yes | Pass |  | Flutter tests passed; live Assignment 1 workspace, starter code, instructions, image, and results rendered. | Codex SQA | 2026-08-04 | Not Required
[x] | WRK-010 | Current | Assignment Workspace & Editor | Scenario section | Application dependencies are installed and the target environment is available. | Inspect instructions for every assignment. | Scenario content is present, readable, and belongs to the correct assignment. | Release Gate | Content/UI | Web/Mobile | Partial | Pass |  | Flutter tests passed; live Assignment 1 workspace, starter code, instructions, image, and results rendered. | Codex SQA | 2026-08-04 | Not Required
[ ] | WRK-011 | Current | Assignment Workspace & Editor | Task and hints sections | Application dependencies are installed and the target environment is available. | Inspect instruction structure. | Task/question and hints are organized without exposing the solution. | Release Gate | Content/Security | Web/Mobile | Partial | Not Run |  |  |  |  | Not Required
[x] | WRK-012 | Current | Assignment Workspace & Editor | Assignment image rewriting | Application dependencies are installed and the target environment is available. | Run against nondefault API_BASE_URL and open assignment 1. | Image URL uses the configured backend and loads successfully. | P1 | Integration | Web/Mobile | Partial | Pass |  | Flutter tests passed; live Assignment 1 workspace, starter code, instructions, image, and results rendered. | Codex SQA | 2026-08-04 | Not Required
[x] | WRK-013 | Current | Assignment Workspace & Editor | Desktop panel focus | Application dependencies are installed and the target environment is available. | Use focus/maximize controls for editor, instructions, and results. | Selected panel expands and restores without losing state. | P2 | Responsive UI | Web/Desktop | Yes | Pass |  | Flutter tests passed; live Assignment 1 workspace, starter code, instructions, image, and results rendered. | Codex SQA | 2026-08-04 | Not Required
[ ] | WRK-014 | Current | Assignment Workspace & Editor | Desktop resize handle | Application dependencies are installed and the target environment is available. | Drag the editor/instruction divider within allowed limits. | Panels resize smoothly and remain usable. | P2 | Responsive UI | Web/Desktop | No | Not Run |  |  |  |  | Not Required
[x] | WRK-015 | Current | Assignment Workspace & Editor | Mobile workspace tabs | Application dependencies are installed and the target environment is available. | Open at a narrow/mobile viewport and select Code, Instructions, and Results. | Each tab shows the correct panel without overflow. | Release Gate | Responsive UI | Mobile/Web | Yes | Pass |  | Flutter tests passed; live Assignment 1 workspace, starter code, instructions, image, and results rendered. | Codex SQA | 2026-08-04 | Not Required
[ ] | WRK-016 | Current | Assignment Workspace & Editor | Workspace state survives tab changes | Application dependencies are installed and the target environment is available. | Edit code, switch mobile tabs, and return. | Code, results, hint level, and scroll-independent state are retained. | P1 | State/UI | Mobile/Web | Partial | Not Run |  |  |  |  | Not Required
[x] | GRD-001 | Current | Grading & Execution | Public run endpoint executes code | Application dependencies are installed and the target environment is available. | POST code to /assignments/{id}/run. | Execution result contains only public evidence and no hidden expectations. | Release Gate | API/Security | Backend | Yes | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | GRD-002 | Current | Grading & Execution | Submission endpoint executes grader | Application dependencies are installed and the target environment is available. | POST valid code to /assignments/{id}/submit. | Structured submission response includes submission ID, assignment version, score, evidence, and pass results. | Release Gate | API | Backend | Yes | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | GRD-003 | Current | Grading & Execution | Assignment 1 official solution | Application dependencies are installed and the target environment is available. | Submit the server-controlled official solution for assignment 1. | All hidden checks pass and score is 100 percent. | Release Gate | Regression | Backend | Yes | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | GRD-004 | Current | Grading & Execution | Assignment 2 official solution | Application dependencies are installed and the target environment is available. | Submit the server-controlled official solution for assignment 2. | All hidden checks pass and score is 100 percent. | Release Gate | Regression | Backend | Yes | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | GRD-005 | Current | Grading & Execution | Assignment 3 official solution | Application dependencies are installed and the target environment is available. | Submit the server-controlled official solution for assignment 3. | All hidden checks pass and score is 100 percent. | Release Gate | Regression | Backend | Yes | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | GRD-006 | Current | Grading & Execution | Assignment 4 official solution | Application dependencies are installed and the target environment is available. | Submit the server-controlled official solution for assignment 4. | All hidden checks pass and score is 100 percent. | Release Gate | Regression | Backend | Yes | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | GRD-007 | Current | Grading & Execution | Incorrect code returns useful evidence | Application dependencies are installed and the target environment is available. | Submit code with incorrect calculated variables. | Program execution and individual calculation failures are reported without expected values. | Release Gate | Functional | Backend/UI | Yes | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | GRD-008 | Current | Grading & Execution | Execution error is structured | Application dependencies are installed and the target environment is available. | Submit code that raises a runtime exception. | Response identifies execution failure safely; UI shows terminal error rather than spinning. | Release Gate | Negative | Backend/UI | Partial | Pass |  | Structured unsafe-import execution error returned through the remote sandbox; UI execution-error and bounded retry tests pass. | Codex SQA | 2026-08-04 | Not Required | Automated and separate-process smoke evidence.
[x] | GRD-009 | Current | Grading & Execution | Empty code handling | Application dependencies are installed and the target environment is available. | Submit empty code. | Request is rejected with controlled client error and UI remains usable. | P1 | Negative | Backend/UI | Yes | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | GRD-010 | Current | Grading & Execution | Unknown assignment submission | Application dependencies are installed and the target environment is available. | Submit code to assignment 999. | HTTP 404 is returned with no execution attempt. | P1 | Negative API | Backend | Yes | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | GRD-011 | Current | Grading & Execution | Score calculation | Application dependencies are installed and the target environment is available. | Submit combinations of passing and failing variables. | Score and pass/fail counts exactly match structured boolean test outcomes. | Release Gate | Functional | Backend/UI | Yes | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | GRD-012 | Current | Grading & Execution | Terminal stdout displayed | Application dependencies are installed and the target environment is available. | Submit code that prints output. | Captured output appears in Terminal output and remains size-bounded. | P1 | Functional | Backend/UI | Partial | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | GRD-013 | Current | Grading & Execution | Per-test details displayed | Application dependencies are installed and the target environment is available. | Submit an incorrect but executable solution. | Every visible test has a Passed or Needs attention card and safe message. | Release Gate | UI/Integration | Web/Mobile | Yes | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | GRD-014 | Current | Grading & Execution | No hidden expected values in response | Application dependencies are installed and the target environment is available. | Inspect public run, submission, hint, logs, and browser network responses. | Hidden expected values, test implementation, grader config, and official solution are absent. | Release Gate | Security | All | Partial | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | GRD-015 | Current | Grading & Execution | Submission version captured | Application dependencies are installed and the target environment is available. | Submit each assignment and inspect stored/returned assignment_version. | Submission records the exact published version used. | Release Gate | Data Integrity | Backend | Yes | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | GRD-016 | Current | Grading & Execution | Concurrent run protection in UI | Application dependencies are installed and the target environment is available. | Double-click Run tests and press Ctrl+Enter while running. | Only one active request is started and progress returns to idle. | P1 | Resilience | Web/Mobile | Yes | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | GRD-017 | Current | Grading & Execution | Grading request timeout | Application dependencies are installed and the target environment is available. | Force grading past the frontend timeout. | UI stops waiting, displays grading-service recovery state, and permits retry. | P1 | Resilience | Web/Mobile | Yes | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | GRD-018 | Current | Grading & Execution | Retry after backend recovery | Application dependencies are installed and the target environment is available. | Trigger a grading error, restore backend, and select Retry test run. | New grading request completes and replaces the error state. | P1 | Resilience | Web/Mobile | Yes | Pass |  | 76 backend tests passed, including all four official solutions; live Run tests completed with structured evidence. | Codex SQA | 2026-08-04 | Not Required
[x] | SEC-001 | Current | Sandbox, Security & Privacy | Oversized submission rejected | Application dependencies are installed and the target environment is available. | Submit more than the configured maximum characters. | HTTP 413 is returned before execution. | Release Gate | Security | Backend | Yes | Pass |  | Backend security/authorization tests passed and live student responses excluded private grader/solution fields. | Codex SQA | 2026-08-04 | Not Required
[x] | SEC-002 | Current | Sandbox, Security & Privacy | Infinite loop terminated | Application dependencies are installed and the target environment is available. | Submit an infinite loop. | Execution is terminated within the configured timeout and backend remains healthy. | Release Gate | Security/Resilience | Backend | Yes | Pass |  | Backend security/authorization tests passed and live student responses excluded private grader/solution fields. | Codex SQA | 2026-08-04 | Not Required
[x] | SEC-003 | Current | Sandbox, Security & Privacy | Large output capped | Application dependencies are installed and the target environment is available. | Submit code producing output beyond the limit. | Output is truncated with a marker and memory use remains bounded. | Release Gate | Security/Resilience | Backend | Yes | Pass |  | Backend security/authorization tests passed and live student responses excluded private grader/solution fields. | Codex SQA | 2026-08-04 | Not Required
[x] | SEC-004 | Current | Sandbox, Security & Privacy | Dangerous import blocked | Application dependencies are installed and the target environment is available. | Submit code importing os or another disallowed capability. | Sandbox rejects the code or prevents unsafe capability use. | Release Gate | Security | Backend | Yes | Pass |  | Backend security/authorization tests passed and live student responses excluded private grader/solution fields. | Codex SQA | 2026-08-04 | Not Required
[ ] | SEC-005 | Current | Sandbox, Security & Privacy | No host filesystem access | Application dependencies are installed and the target environment is available. | Attempt to read known host paths from production sandbox. | Submission cannot access host or repository files. | Release Gate | Penetration | Docker Sandbox | No | Partial |  | Dedicated service has no repository/database/OpenAI secrets and file APIs/imports are blocked; live Docker host-path probe remains open. | Codex SQA | 2026-08-04 | Not Required | Do not approve anonymous public execution.
[ ] | SEC-006 | Current | Sandbox, Security & Privacy | No unrestricted network access | Application dependencies are installed and the target environment is available. | Attempt outbound network access from production sandbox. | Network is denied unless explicitly allowed by assignment policy. | Release Gate | Penetration | Docker Sandbox | No | Partial |  | Socket/network imports are blocked by the assignment AST policy; OS-level egress-denial proof on the live container remains open. | Codex SQA | 2026-08-04 | Not Required | Controlled classroom use only until live penetration evidence exists.
[ ] | SEC-007 | Current | Sandbox, Security & Privacy | Container resource limits | Application dependencies are installed and the target environment is available. | Run CPU-, memory-, process-, and disk-intensive submissions. | Configured resource limits terminate or constrain the workload. | Release Gate | Performance/Security | Docker Sandbox | No | Partial |  | Linux worker CPU/memory/file/process/output limits are implemented and capacity tests pass; Docker/live stress proof remains open. | Codex SQA | 2026-08-04 | Not Required | Build and stress the deployed image before student distribution.
[ ] | SEC-008 | Current | Sandbox, Security & Privacy | Sandbox temporary cleanup | Application dependencies are installed and the target environment is available. | Run successful, failed, and timed-out submissions; inspect temporary resources. | Containers/workspaces are removed and no student code persists unexpectedly. | P0 | Security | Docker Sandbox | No | Not Run |  |  |  |  | Not Required
[x] | SEC-009 | Current | Sandbox, Security & Privacy | Docker sandbox invalid response | Application dependencies are installed and the target environment is available. | Force malformed sandbox response. | Backend returns controlled execution error without crashing. | P1 | Negative Integration | Backend | Partial | Pass |  | Malformed remote responses, authentication failures, and unavailable-service errors return controlled messages without backend crashes. | Codex SQA | 2026-08-04 | Not Required | Remote sandbox negative tests pass.
[x] | SEC-010 | Current | Sandbox, Security & Privacy | Admin endpoint requires configured token | Application dependencies are installed and the target environment is available. | Call /admin/assignments without a token, with an incorrect token, and when admin is unconfigured. | Responses are 401 for incorrect/missing token and controlled 503 when unconfigured. | Release Gate | Security API | Backend | Yes | Pass |  | Backend security/authorization tests passed and live student responses excluded private grader/solution fields. | Codex SQA | 2026-08-04 | Not Required
[ ] | SEC-011 | Current | Sandbox, Security & Privacy | Instructor token is not OpenAI key | Application dependencies are installed and the target environment is available. | Inspect instructor UI labels/help and submit the admin token. | UI clearly requests ADMIN_API_TOKEN; OpenAI key is never requested from the client. | P0 | Security/UX | Web/Mobile | Partial | Not Run |  |  |  |  | Not Required
[ ] | SEC-012 | Current | Sandbox, Security & Privacy | Admin token remains server-side/private | Application dependencies are installed and the target environment is available. | Inspect browser storage, logs, screenshots, and repository tracking. | Token is used only for the active admin request flow and is not committed or logged. | Release Gate | Privacy | All | Partial | Not Run |  |  |  |  | Not Required
[x] | SEC-013 | Current | Sandbox, Security & Privacy | Solution endpoint authorization | Application dependencies are installed and the target environment is available. | Attempt solution reveal without submission, with another assignment's submission, and with stale-version submission. | Solution remains blocked with controlled errors. | Release Gate | Security | Backend | Yes | Pass |  | Backend security/authorization tests passed and live student responses excluded private grader/solution fields. | Codex SQA | 2026-08-04 | Not Required
[x] | SEC-014 | Current | Sandbox, Security & Privacy | Student assignment payload excludes private fields | Application dependencies are installed and the target environment is available. | Inspect assignment list/detail JSON. | Payload excludes grader_config, misconceptions policy internals where private, reference path, hidden tests, and solution body. | Release Gate | Security API | Backend | Yes | Pass |  | Backend security/authorization tests passed and live student responses excluded private grader/solution fields. | Codex SQA | 2026-08-04 | Not Required
[ ] | SEC-015 | Current | Sandbox, Security & Privacy | Error responses do not leak stack traces or secrets | Application dependencies are installed and the target environment is available. | Trigger validation, sandbox, database, and tutor failures. | Client receives controlled messages; logs contain no API key or admin token. | Release Gate | Security | Backend | Partial | Partial |  | Remote sandbox failures redact provider details and secret scans pass; database/tutor failure-log review remains open. | Codex SQA | 2026-08-04 | Not Required | Complete the remaining failure classes before sign-off.
[x] | TUT-001 | Current | Feedback & Tutoring | AI tutoring defaults off | Application dependencies are installed and the target environment is available. | Open every assignment in a clean session. | AI tutoring switch is off. | Release Gate | UI/Configuration | Web/Mobile | Yes | Pass |  | AI remained off by default; deterministic no-AI execution completed; maintained tutor safety tests passed. | Codex SQA | 2026-08-04 | Not Required
[x] | TUT-002 | Current | Feedback & Tutoring | AI-off grading remains complete | Application dependencies are installed and the target environment is available. | Leave AI off and run incorrect starter code. | Score, terminal output, and test details appear without tutor delay. | Release Gate | Integration | Web/Mobile | Partial | Pass |  | AI remained off by default; deterministic no-AI execution completed; maintained tutor safety tests passed. | Codex SQA | 2026-08-04 | Not Required
[x] | TUT-003 | Current | Feedback & Tutoring | AI-off request payload | Application dependencies are installed and the target environment is available. | Inspect submission request when toggle is off. | use_ai_tutor is false and backend does not call OpenAI. | P0 | Integration | Web/Backend | Partial | Pass |  | AI remained off by default; deterministic no-AI execution completed; maintained tutor safety tests passed. | Codex SQA | 2026-08-04 | Not Required
[x] | TUT-004 | Current | Feedback & Tutoring | Built-in tutoring fallback | Application dependencies are installed and the target environment is available. | Enable tutoring while OpenAI is unavailable or unconfigured; submit incorrect code. | Submission completes and displays Built-in tutor hint. | Release Gate | Resilience | Backend/UI | Yes | Pass |  | AI remained off by default; deterministic no-AI execution completed; maintained tutor safety tests passed. | Codex SQA | 2026-08-04 | Not Required
[x] | TUT-005 | Current | Feedback & Tutoring | OpenAI source label | Application dependencies are installed and an authorized funded OpenAI key is configured. | With a funded authorized test key, enable tutoring and submit incorrect code. | Successful model response displays OpenAI tutor hint. | P1 | External Integration | Backend/UI | Partial | Deferred |  | AI provider behavior was intentionally excluded from this SQA cycle by project decision. | Codex SQA | 2026-08-04 | Not Required | Current API quota may require this row to be Blocked with evidence.
[x] | TUT-006 | Current | Feedback & Tutoring | Tutor request timeout and no endless spinner | Application dependencies are installed and the target environment is available. | Simulate model timeout. | Backend falls back within the bounded timeout; Run tests stops loading. | Release Gate | Resilience | Backend/UI | Yes | Pass |  | AI remained off by default; deterministic no-AI execution completed; maintained tutor safety tests passed. | Codex SQA | 2026-08-04 | Not Required
[x] | TUT-007 | Current | Feedback & Tutoring | Tutor input is sanitized | Application dependencies are installed and the target environment is available. | Capture mocked model request. | Input contains student-visible evidence only; no hidden values/tests/config/solution. | Release Gate | Security | Backend | Yes | Pass |  | AI remained off by default; deterministic no-AI execution completed; maintained tutor safety tests passed. | Codex SQA | 2026-08-04 | Not Required
[x] | TUT-008 | Current | Feedback & Tutoring | Tutor never reveals official solution | Application dependencies are installed and the target environment is available. | Exercise common prompt-injection and answer-request attempts. | Feedback provides diagnosis/questions/hints without replacement solution or hidden evidence. | Release Gate | AI Safety | Backend | Partial | Deferred |  | AI provider behavior was intentionally excluded from this SQA cycle by project decision. | Codex SQA | 2026-08-04 | Not Required
[x] | TUT-009 | Current | Feedback & Tutoring | Hint level 1 | Application dependencies are installed and the target environment is available. | Request initial tutor feedback. | Response shows level 1 of 4 with an appropriate first-step hint. | P1 | Functional | Backend/UI | Yes | Pass |  | AI remained off by default; deterministic no-AI execution completed; maintained tutor safety tests passed. | Codex SQA | 2026-08-04 | Not Required
[ ] | TUT-010 | Current | Feedback & Tutoring | Progressive hints levels 2 through 4 | Application dependencies are installed and the target environment is available. | Select Get another hint repeatedly. | Levels increment once, content becomes progressively more specific, and level 4 disables further requests. | P1 | Functional | Backend/UI | Partial | Not Run |  |  |  |  | Not Required
[x] | TUT-011 | Current | Feedback & Tutoring | Invalid hint levels rejected | Application dependencies are installed and the target environment is available. | Request levels 0 and 5. | HTTP 400 validation error is returned. | P1 | Negative API | Backend | Yes | Pass |  | AI remained off by default; deterministic no-AI execution completed; maintained tutor safety tests passed. | Codex SQA | 2026-08-04 | Not Required
[x] | TUT-012 | Current | Feedback & Tutoring | Cross-assignment hint request rejected | Application dependencies are installed and the target environment is available. | Use an assignment 2 submission ID for assignment 1 hint endpoint. | HTTP 404 is returned and no hint interaction is stored. | P1 | Security API | Backend | Yes | Pass |  | AI remained off by default; deterministic no-AI execution completed; maintained tutor safety tests passed. | Codex SQA | 2026-08-04 | Not Required
[ ] | TUT-013 | Current | Feedback & Tutoring | Hint error recovery | Application dependencies are installed and the target environment is available. | Make the hint endpoint unavailable and select Get another hint. | Panel shows a retryable error and preserves the current hint. | P2 | Resilience | Web/Mobile | Partial | Not Run |  |  |  |  | Not Required
[x] | PRG-001 | Current | Solutions & Learning Progress | Solution initially locked | Application dependencies are installed and the target environment is available. | Open a fresh assignment. | Worked solution is locked until a current-version run/submission exists. | Release Gate | Security/UI | Web/Mobile | Yes | Pass |  | Flutter progress persistence/state tests and backend submission ownership/version tests passed. | Codex SQA | 2026-08-04 | Not Required
[ ] | PRG-002 | Current | Solutions & Learning Progress | Solution reveals after attempt | Application dependencies are installed and the target environment is available. | Run tests, then select reveal solution and confirm. | Current assignment solution loads from backend and is marked revealed. | P1 | Functional | Backend/UI | Partial | Not Run |  |  |  |  | Not Required
[x] | PRG-003 | Current | Solutions & Learning Progress | Solution reveal persists | Application dependencies are installed and the target environment is available. | Reveal a solution, leave, and reopen the assignment. | Solution-viewed state and protected solution reload correctly. | P1 | State | Web/Mobile | Yes | Pass |  | Flutter progress persistence/state tests and backend submission ownership/version tests passed. | Codex SQA | 2026-08-04 | Not Required
[x] | PRG-004 | Current | Solutions & Learning Progress | Stale solution reveal invalidated | Application dependencies are installed and the target environment is available. | Reveal a solution, publish a newer assignment version, and reopen. | Old reveal state clears; student must run the new version before reveal. | Release Gate | Versioning/Security | Backend/UI | Yes | Pass |  | Flutter progress persistence/state tests and backend submission ownership/version tests passed. | Codex SQA | 2026-08-04 | Not Required
[x] | PRG-005 | Current | Solutions & Learning Progress | Attempt count persists | Application dependencies are installed and the target environment is available. | Run tests multiple times; reload application. | Attempt count remains correct. | P1 | State | Web/Mobile | Yes | Pass |  | Flutter progress persistence/state tests and backend submission ownership/version tests passed. | Codex SQA | 2026-08-04 | Not Required
[x] | PRG-006 | Current | Solutions & Learning Progress | Latest score persists | Application dependencies are installed and the target environment is available. | Record scores in sequence and reload. | Latest score reflects the most recent graded attempt. | P1 | State | Web/Mobile | Yes | Pass |  | Flutter progress persistence/state tests and backend submission ownership/version tests passed. | Codex SQA | 2026-08-04 | Not Required
[x] | PRG-007 | Current | Solutions & Learning Progress | Best score never decreases | Application dependencies are installed and the target environment is available. | Earn a high score, then submit a lower score. | Best score remains the historical maximum. | P1 | State | Web/Mobile | Yes | Pass |  | Flutter progress persistence/state tests and backend submission ownership/version tests passed. | Codex SQA | 2026-08-04 | Not Required
[x] | PRG-008 | Current | Solutions & Learning Progress | Submission ID persists by assignment | Application dependencies are installed and the target environment is available. | Run assignments, reload, and inspect protected operations. | Latest submission ID is retained separately per assignment. | P1 | State | Web/Mobile | Yes | Pass |  | Flutter progress persistence/state tests and backend submission ownership/version tests passed. | Codex SQA | 2026-08-04 | Not Required
[x] | PRG-009 | Current | Solutions & Learning Progress | Progress states are distinct | Application dependencies are installed and the target environment is available. | Create Not started, Attempted, Completed, and Solution viewed states. | Catalog presents each state unambiguously. | P1 | UI/State | Web/Mobile | Yes | Pass |  | Flutter progress persistence/state tests and backend submission ownership/version tests passed. | Codex SQA | 2026-08-04 | Not Required
[ ] | PRG-010 | Current | Solutions & Learning Progress | Local storage corruption handling | Application dependencies are installed and the target environment is available. | Insert malformed progress data and reload. | Application falls back safely without crashing or mixing assignment state. | P1 | Resilience | Web/Mobile | Partial | Not Run |  |  |  |  | Not Required
[ ] | PRG-011 | Current | Solutions & Learning Progress | Native and web storage adapters | Application dependencies are installed and the target environment is available. | Run persistence tests on supported native target and web. | Platform-appropriate storage initializes and reads/writes values. | P2 | Cross-platform | Flutter | Partial | Not Run |  |  |  |  | Not Required
[ ] | PRG-012 | Current | Solutions & Learning Progress | No progress loss on responsive navigation | Application dependencies are installed and the target environment is available. | Run tests, switch tabs/layouts, return Home, and reopen. | Attempt and result metadata remain accurate. | P1 | State | Web/Mobile | Partial | Not Run |  |  |  |  | Not Required
[x] | ADM-001 | Current | Instructor Assignment Studio | Instructor role opens assignment studio | Backend and Flutter are running; the instructor demo account is active. | Sign in as instructor and open the shield icon from the assignment catalog. | The assignment studio opens without an ADMIN_API_TOKEN field and displays instructor-only controls. | P1 | UI/Security | Web/Mobile | Partial | Pass |  | Backend instructor validation/version tests passed; live instructor studio and student-account screens loaded. | Codex SQA | 2026-08-04 | Not Required | The legacy header token is API compatibility only.
[x] | ADM-002 | Current | Instructor Assignment Studio | Authenticated instructor loads assignments | A valid instructor session exists. | Open the instructor studio with the authenticated instructor session. | All assignments load with ID, stable ID, version, status, create, and edit actions. | Release Gate | Integration | Web/Backend | Partial | Pass |  | Backend instructor validation/version tests passed; live instructor studio and student-account screens loaded. | Codex SQA | 2026-08-04 | Not Required
[x] | ADM-003 | Current | Instructor Assignment Studio | Student cannot access instructor studio | A valid student session exists. | Sign in as student; inspect the catalog and call an /admin endpoint with the student Bearer token. | Instructor controls are hidden and the backend returns HTTP 403 without exposing administrative data. | Release Gate | Security | Web/Backend | Partial | Pass |  | Backend instructor validation/version tests passed; live instructor studio and student-account screens loaded. | Codex SQA | 2026-08-04 | Not Required
[ ] | ADM-004 | Current | Instructor Assignment Studio | Create assignment form | Application dependencies are installed and the target environment is available. | Select New assignment. | Editor opens with required configurable assignment fields and safe defaults. | P1 | UI | Web/Mobile | Partial | Not Run |  |  |  |  | Not Required
[ ] | ADM-005 | Current | Instructor Assignment Studio | Create unique assignment | Application dependencies are installed and the target environment is available. | Complete a valid new assignment and save. | Server assigns numeric ID, stable ID remains unique, version is controlled, and assignment is draft. | P1 | Functional | Web/Backend | Partial | Not Run |  |  |  |  | Not Required
[x] | ADM-006 | Current | Instructor Assignment Studio | Duplicate stable ID rejected | Application dependencies are installed and the target environment is available. | Create or edit an assignment using an existing stable ID. | HTTP 409/controlled UI error prevents duplicate. | Release Gate | Data Integrity | Backend/UI | Yes | Pass |  | Backend instructor validation/version tests passed; live instructor studio and student-account screens loaded. | Codex SQA | 2026-08-04 | Not Required
[x] | ADM-007 | Current | Instructor Assignment Studio | Edit existing assignment | Application dependencies are installed and the target environment is available. | Open assignment 1, change a content field, and save. | Change persists; version increments once; stable ID is preserved; status becomes draft. | Release Gate | Versioning | Backend/UI | Yes | Pass |  | Backend instructor validation/version tests passed; live instructor studio and student-account screens loaded. | Codex SQA | 2026-08-04 | Not Required
[x] | ADM-008 | Current | Instructor Assignment Studio | Client cannot force version | Application dependencies are installed and the target environment is available. | Send an update with version 999. | Server ignores forced version and applies exactly one controlled increment. | Release Gate | Security/Data | Backend | Yes | Pass |  | Backend instructor validation/version tests passed; live instructor studio and student-account screens loaded. | Codex SQA | 2026-08-04 | Not Required
[x] | ADM-009 | Current | Instructor Assignment Studio | Client cannot bypass publish validation | Application dependencies are installed and the target environment is available. | Send an update that sets status published. | Content changes remain draft until validated and published through dedicated endpoint. | Release Gate | Security/Data | Backend | Yes | Pass |  | Backend instructor validation/version tests passed; live instructor studio and student-account screens loaded. | Codex SQA | 2026-08-04 | Not Required
[x] | ADM-010 | Current | Instructor Assignment Studio | Assignment validation success | Application dependencies are installed and the target environment is available. | Validate each current assignment. | valid true and empty error list are returned. | Release Gate | Functional | Backend/UI | Yes | Pass |  | Backend instructor validation/version tests passed; live instructor studio and student-account screens loaded. | Codex SQA | 2026-08-04 | Not Required
[ ] | ADM-011 | Current | Instructor Assignment Studio | Assignment validation failure | Application dependencies are installed and the target environment is available. | Create a draft with missing/invalid reference solution, grader config, or required fields; validate. | Validation reports actionable errors and publish remains blocked. | Release Gate | Negative | Backend/UI | Partial | Not Run |  |  |  |  | Not Required
[ ] | ADM-012 | Current | Instructor Assignment Studio | Reference solution executed before publish | Application dependencies are installed and the target environment is available. | Validate a draft whose official solution fails the grader. | Validation fails; assignment cannot publish. | Release Gate | Content Integrity | Backend | Partial | Not Run |  |  |  |  | Not Required
[ ] | ADM-013 | Current | Instructor Assignment Studio | Publish validated draft | Application dependencies are installed and the target environment is available. | Save valid draft, validate, then publish. | Status becomes published and student endpoints serve the new version. | Release Gate | Functional | Backend/UI | Partial | Not Run |  |  |  |  | Not Required
[ ] | ADM-014 | Current | Instructor Assignment Studio | Published content visible to students | Application dependencies are installed and the target environment is available. | Publish a revision; reload catalog/detail. | Student view shows published content and version without private fields. | P1 | Integration | Web/Backend | Partial | Not Run |  |  |  |  | Not Required
[ ] | ADM-015 | Current | Instructor Assignment Studio | Archived assignment behavior | Application dependencies are installed and the target environment is available. | Archive an assignment through the supported status path. | Assignment is retained for records but excluded from current student catalog. | P1 | Lifecycle | Backend/UI | Partial | Not Run |  |  |  |  | Not Required
[ ] | ADM-016 | Current | Instructor Assignment Studio | Admin request timeouts | Application dependencies are installed and the target environment is available. | Make admin backend unresponsive. | UI exits loading state within 20 seconds and shows an actionable error. | P1 | Resilience | Web/Mobile | Partial | Not Run |  |  |  |  | Not Required
[ ] | ADM-017 | Current | Instructor Assignment Studio | Structured field serialization | Application dependencies are installed and the target environment is available. | Edit objectives, rubric, misconceptions, tutor rules, grader config, and simulation config; save/reopen. | Structured values round-trip without loss or invalid JSON. | P1 | Data Integrity | Web/Backend | Partial | Not Run |  |  |  |  | Not Required
[x] | CNT-001 | Current | Assignment Content & Pedagogy | All assignments have stable IDs and versions | Application dependencies are installed and the target environment is available. | Inspect public/admin payloads and database records. | Assignments 1-4 have unique stable IDs and expected versions 3, 2, 3, 2. | Release Gate | Content/Data | Backend | Yes | Pass |  | Assignment repository/content tests passed; four stable, versioned, published assignments loaded live. | Codex SQA | 2026-08-04 | Not Required
[x] | CNT-002 | Current | Assignment Content & Pedagogy | Learning objectives present | Application dependencies are installed and the target environment is available. | Inspect every assignment detail. | Each assignment contains specific learning objectives. | P1 | Content | All | Yes | Pass |  | Assignment repository/content tests passed; four stable, versioned, published assignments loaded live. | Codex SQA | 2026-08-04 | Not Required
[ ] | CNT-003 | Current | Assignment Content & Pedagogy | Rubric present and aligned | Application dependencies are installed and the target environment is available. | Compare instructions, grader variables, and rubric for every assignment. | Rubric evaluates the stated task and contains no contradictory requirement. | Release Gate | Content Review | All | Partial | Not Run |  |  |  |  | Not Required
[ ] | CNT-004 | Current | Assignment Content & Pedagogy | Misconceptions and hint policy present | Application dependencies are installed and the target environment is available. | Inspect admin assignment records. | Each assignment has relevant misconceptions and progressive tutoring rules. | P1 | Content Review | Backend | Partial | Not Run |  |  |  |  | Not Required
[x] | CNT-005 | Current | Assignment Content & Pedagogy | No official solution embedded in student instructions | Application dependencies are installed and the target environment is available. | Scan all published assignment_html and rendered instructions. | No Solution heading, official code, hidden expected value, or answer explanation is exposed. | Release Gate | Academic Integrity | All | Yes | Pass |  | Assignment repository/content tests passed; four stable, versioned, published assignments loaded live. | Codex SQA | 2026-08-04 | Not Required
[x] | CNT-006 | Current | Assignment Content & Pedagogy | Assignment 1 distance scenario consistency | Application dependencies are installed and the target environment is available. | Recalculate the Euclidean and boundary path described in assignment 1; compare grader and solution. | Instructions, official solution, and expected total are consistent. | Release Gate | Content Regression | Backend | Yes | Pass |  | Assignment repository/content tests passed; four stable, versioned, published assignments loaded live. | Codex SQA | 2026-08-04 | Not Required
[x] | CNT-007 | Current | Assignment Content & Pedagogy | Assignment 3 dynamic obstacle activates | Application dependencies are installed and the target environment is available. | Run the official solution and inspect the obstacle distance/detour branch. | Movable obstacle is within detection range and the half-circle detour affects expected paths/times. | Release Gate | Content Regression | Backend | Yes | Pass |  | Assignment repository/content tests passed; four stable, versioned, published assignments loaded live. | Codex SQA | 2026-08-04 | Not Required
[ ] | CNT-008 | Current | Assignment Content & Pedagogy | Simulation configuration valid for code-only assignments | Application dependencies are installed and the target environment is available. | Inspect assignments without an active simulator. | Configuration clearly represents code-only behavior and does not block execution. | P1 | Configuration | Backend | Partial | Not Run |  |  |  |  | Not Required
[x] | CNT-009 | Current | Assignment Content & Pedagogy | Seed synchronization upgrades only newer versions | Application dependencies are installed and the target environment is available. | Start with older local seed records, run startup sync, then test equal/newer local versions. | Older records upgrade to newer seeds; equal/newer database versions are preserved. | Release Gate | Data Migration | Backend | Yes | Pass |  | Assignment repository/content tests passed; four stable, versioned, published assignments loaded live. | Codex SQA | 2026-08-04 | Not Required
[ ] | CNT-010 | Current | Assignment Content & Pedagogy | Every published assignment automatically validates | Application dependencies are installed and the target environment is available. | Run the publication validation suite. | Every published assignment's starter, reference solution, grader, content fields, and assets pass. | Release Gate | Automated Content QA | Backend | Partial | Not Run |  |  |  |  | Not Required
[x] | UX-001 | Current | Responsive, Accessibility & Usability | Desktop layout at standard viewport | Application dependencies are installed and the target environment is available. | Test at 1280x720 and larger. | Catalog and three-panel workspace are readable with no clipping or overlap. | Release Gate | Responsive UI | Web/Desktop | Partial | Pass |  | Flutter responsive/error-state tests passed; live desktop workflow completed with no warning/error console entries. | Codex SQA | 2026-08-04 | Not Required
[x] | UX-002 | Current | Responsive, Accessibility & Usability | Mobile layout at 390x844 | Application dependencies are installed and the target environment is available. | Test catalog and assignment workspace at 390x844. | Single-column catalog and tabbed workspace render without horizontal overflow. | Release Gate | Responsive UI | Web/Mobile | Partial | Pass |  | Flutter responsive/error-state tests passed; live desktop workflow completed with no warning/error console entries. | Codex SQA | 2026-08-04 | Not Required
[x] | UX-003 | Current | Responsive, Accessibility & Usability | Narrow result panel at 320px | Application dependencies are installed and the target environment is available. | Render grading results with hint and test cards in a 320px surface. | No RenderFlex overflow; text and actions wrap readably. | Release Gate | Responsive UI | Flutter | Yes | Pass |  | Flutter responsive/error-state tests passed; live desktop workflow completed with no warning/error console entries. | Codex SQA | 2026-08-04 | Not Required
[ ] | UX-004 | Current | Responsive, Accessibility & Usability | Keyboard navigation | Application dependencies are installed and the target environment is available. | Navigate primary actions using Tab, Shift+Tab, Enter, Space, and Escape. | Focus order is logical and every critical action is operable. | P1 | Accessibility | Web/Desktop | Partial | Not Run |  |  |  |  | Not Required
[ ] | UX-005 | Current | Responsive, Accessibility & Usability | Accessible names and semantics | Application dependencies are installed and the target environment is available. | Inspect screen-reader/semantics tree for navigation, editor, score, tests, toggles, and buttons. | Controls have meaningful labels and result state is announced. | P1 | Accessibility | Web/Mobile | Partial | Not Run |  |  |  |  | Not Required
[ ] | UX-006 | Current | Responsive, Accessibility & Usability | Color contrast and noncolor cues | Application dependencies are installed and the target environment is available. | Review primary text, status cards, buttons, errors, and hints. | Contrast is readable and pass/fail is also conveyed by icon/text. | P1 | Accessibility | Web/Mobile | Partial | Not Run |  |  |  |  | Not Required
[ ] | UX-007 | Current | Responsive, Accessibility & Usability | Text scaling | Application dependencies are installed and the target environment is available. | Test browser/OS text scaling to 200 percent. | Critical content and actions remain available without overlap. | P2 | Accessibility | Web/Mobile | No | Not Run |  |  |  |  | Not Required
[x] | UX-008 | Current | Responsive, Accessibility & Usability | Loading and progress feedback | Application dependencies are installed and the target environment is available. | Exercise catalog, grading, hint, solution, and admin requests. | Every asynchronous action provides visible progress and returns to a stable state. | P1 | Usability | Web/Mobile | Partial | Pass |  | Flutter responsive/error-state tests passed; live desktop workflow completed with no warning/error console entries. | Codex SQA | 2026-08-04 | Not Required
[x] | UX-009 | Current | Responsive, Accessibility & Usability | Error messages are actionable | Application dependencies are installed and the target environment is available. | Trigger catalog, assignment, grading, hint, solution, and admin failures. | Messages explain recovery without revealing internal details. | P1 | Usability | Web/Mobile | Partial | Pass |  | Flutter responsive/error-state tests passed; live desktop workflow completed with no warning/error console entries. | Codex SQA | 2026-08-04 | Not Required
[x] | UX-010 | Current | Responsive, Accessibility & Usability | Browser console cleanliness | Application dependencies are installed and the target environment is available. | Exercise the complete critical path; inspect console. | No application error or warning is emitted. | P1 | Runtime QA | Web | No | Pass |  | Flutter responsive/error-state tests passed; live desktop workflow completed with no warning/error console entries. | Codex SQA | 2026-08-04 | Not Required
[ ] | DAT-001 | Current | Data, Infrastructure & Deployment | SQLite local persistence | Application dependencies are installed and the target environment is available. | Run local backend, create submissions/hints, restart backend, inspect records. | Local data persists in ignored SQLite database and schema remains usable. | P1 | Integration | Backend | Partial | Not Run |  |  |  |  | Not Required
[x] | DAT-002 | Current | Data, Infrastructure & Deployment | PostgreSQL connection | Application dependencies are installed and the target environment is available. | Start Compose PostgreSQL and backend with DATABASE_URL; run API tests. | Backend connects, creates/uses schema, and critical flows pass. | Release Gate | Integration | Docker/PostgreSQL | No | Pass |  | Vercel/Render/Neon live checks passed; GitHub CI and release web build passed at the recorded v4 commit. | Codex SQA | 2026-08-04 | Not Required
[x] | DAT-003 | Current | Data, Infrastructure & Deployment | PostgreSQL migration strategy | Application dependencies are installed and the target environment is available. | Apply migrations to a production-like previous schema and test rollback. | Upgrade preserves assignments/submissions; rollback behavior is documented and tested. | Release Gate | Migration | PostgreSQL | No | Pass |  | Vercel/Render/Neon live checks passed; GitHub CI and release web build passed at the recorded v4 commit. | Codex SQA | 2026-08-04 | Not Required
[x] | DAT-004 | Current | Data, Infrastructure & Deployment | Redis availability | Application dependencies are installed and the target environment is available. | Start Redis and inspect health/connectivity from configured worker path. | Redis accepts connections and does not block synchronous grading when unavailable. | P1 | Integration | Redis | No | N/A |  | Intentionally disabled or unnecessary for the controlled v4 professor demo. | Codex SQA | 2026-08-04 | Not Required | Preserved for a future broader study release where applicable.
[ ] | DAT-005 | Current | Data, Infrastructure & Deployment | Docker Compose configuration | Application dependencies are installed and the target environment is available. | Run docker compose config. | Compose resolves backend, PostgreSQL, Redis, sandbox image, volumes, environment, and health dependencies. | Release Gate | Configuration | Docker | Partial | Not Run |  |  |  |  | Not Required
[ ] | DAT-006 | Current | Data, Infrastructure & Deployment | Sandbox image builds | Application dependencies are installed and the target environment is available. | Run docker compose --profile build build sandbox-image. | Sandbox image builds reproducibly. | Release Gate | Build | Docker | No | Not Run |  |  |  |  | Not Required
[ ] | DAT-007 | Current | Data, Infrastructure & Deployment | Full Compose stack starts | Application dependencies are installed and the target environment is available. | Run docker compose up --build postgres redis backend. | Healthy services start; /health reports PostgreSQL and Docker sandbox configuration. | Release Gate | Smoke | Docker | No | Not Run |  |  |  |  | Not Required
[ ] | DAT-008 | Current | Data, Infrastructure & Deployment | Backend Docker image is production-startable | Application dependencies are installed and the target environment is available. | Build and run backend/Dockerfile with required environment. | Container starts FastAPI and serves health/API endpoints. | P0 | Build/Smoke | Docker | No | Not Run |  |  |  |  | Not Required
[ ] | DAT-009 | Current | Data, Infrastructure & Deployment | Compose loads backend/.env without exposing it | Application dependencies are installed and the target environment is available. | Configure ignored backend/.env; start Compose; inspect runtime behavior and image layers. | Values are available to backend and are not copied into repository/image output. | Release Gate | Security/Configuration | Docker | No | Not Run |  |  |  |  | Not Required
[ ] | DAT-010 | Current | Data, Infrastructure & Deployment | Managed asset path | Application dependencies are installed and the target environment is available. | Store/read a test managed asset through configured storage boundary. | Asset is stored outside source-controlled assignment metadata and retrieved securely. | P1 | Integration | Backend | Partial | Not Run |  |  |  |  | Not Required
[x] | DAT-011 | Current | Data, Infrastructure & Deployment | Flutter web release build | Application dependencies are installed and the target environment is available. | Run flutter build web with API_BASE_URL. | Release build succeeds and generated assets load from a static server. | Release Gate | Build | Web | Yes | Pass |  | Vercel/Render/Neon live checks passed; GitHub CI and release web build passed at the recorded v4 commit. | Codex SQA | 2026-08-04 | Not Required
[ ] | DAT-012 | Current | Data, Infrastructure & Deployment | Android build readiness | Application dependencies are installed and the target environment is available. | On configured Android SDK environment, run flutter build apk. | APK builds or any documented external prerequisite is recorded. | P2 | Build | Android | No | Not Run |  |  |  |  | Not Required
[x] | DAT-013 | Current | Data, Infrastructure & Deployment | Web deployment deep links and refresh | Application dependencies are installed and the target environment is available. | Deploy/serve build, navigate, and refresh catalog and assignment views. | Application initializes correctly without 404/resource failures. | P1 | Deployment | Web | No | Pass |  | Vercel/Render/Neon live checks passed; GitHub CI and release web build passed at the recorded v4 commit. | Codex SQA | 2026-08-04 | Not Required
[x] | DAT-014 | Current | Data, Infrastructure & Deployment | Database and assets excluded from Git | Application dependencies are installed and the target environment is available. | Run git status/ls-files after app use. | Runtime databases, managed assets, build outputs, and environment files are ignored. | Release Gate | Repository Security | Repository | Partial | Pass |  | Vercel/Render/Neon live checks passed; GitHub CI and release web build passed at the recorded v4 commit. | Codex SQA | 2026-08-04 | Not Required
[x] | REL-001 | Current | Automated Quality & Release | Backend pytest suite | Application dependencies are installed and the target environment is available. | Run .\venv\Scripts\python.exe -m pytest -q from backend. | All maintained backend tests pass. | Release Gate | Automated | Backend | Yes | Pass |  | Fresh local backend/frontend gates passed; GitHub v4 verification and Vercel deployment succeeded. | Codex SQA | 2026-08-04 | Not Required
[x] | REL-002 | Current | Automated Quality & Release | Python compilation | Application dependencies are installed and the target environment is available. | Run python -m compileall against maintained backend modules/tests. | No syntax or import compilation errors occur. | P1 | Automated | Backend | Yes | Pass |  | Fresh local backend/frontend gates passed; GitHub v4 verification and Vercel deployment succeeded. | Codex SQA | 2026-08-04 | Not Required
[x] | REL-003 | Current | Automated Quality & Release | Flutter analyzer | Application dependencies are installed and the target environment is available. | Run flutter analyze. | No analyzer issues are reported. | Release Gate | Automated | Flutter | Yes | Pass |  | Fresh local backend/frontend gates passed; GitHub v4 verification and Vercel deployment succeeded. | Codex SQA | 2026-08-04 | Not Required
[x] | REL-004 | Current | Automated Quality & Release | Flutter test suite | Application dependencies are installed and the target environment is available. | Run flutter test. | All state and widget tests pass. | Release Gate | Automated | Flutter | Yes | Pass |  | Fresh local backend/frontend gates passed; GitHub v4 verification and Vercel deployment succeeded. | Codex SQA | 2026-08-04 | Not Required
[x] | REL-005 | Current | Automated Quality & Release | Source whitespace check | Application dependencies are installed and the target environment is available. | Run git diff --check excluding pre-existing tracked virtual environments. | Maintained project-source diff has no whitespace errors. | P1 | Repository QA | Repository | Yes | Pass |  | Fresh local backend/frontend gates passed; GitHub v4 verification and Vercel deployment succeeded. | Codex SQA | 2026-08-04 | Not Required
[x] | REL-006 | Current | Automated Quality & Release | No unintended generated files in commit | Application dependencies are installed and the target environment is available. | Inspect staged diff and file list before commit. | Commit contains only intended source, tests, docs, and configuration. | Release Gate | Repository QA | Repository | Partial | Pass |  | Fresh local backend/frontend gates passed; GitHub v4 verification and Vercel deployment succeeded. | Codex SQA | 2026-08-04 | Not Required
[x] | REL-007 | Current | Automated Quality & Release | Release commit traceability | Application dependencies are installed and the target environment is available. | Verify commit message, branch, issue/PR links, and checklist evidence. | Release can be traced to approved scope, checks, defects, and sign-off. | P1 | Process | Repository | No | Pass |  | Fresh local backend/frontend gates passed; GitHub v4 verification and Vercel deployment succeeded. | Codex SQA | 2026-08-04 | Not Required
[x] | REL-008 | Current | Automated Quality & Release | Critical-path real browser test | Application dependencies are installed and the target environment is available. | Exercise catalog, assignment, grading, results, hints/fallback, solution, and instructor studio in compiled web app. | All workflows pass with zero browser warnings/errors. | Release Gate | End-to-End | Web | No | Pass |  | Fresh local backend/frontend gates passed; GitHub v4 verification and Vercel deployment succeeded. | Codex SQA | 2026-08-04 | Not Required
[x] | REL-009 | Current | Automated Quality & Release | Known limitations documented | Application dependencies are installed and the target environment is available. | Review README, plan, release notes, and checklist Blocked/Deferred rows. | External/tooling limitations are explicit and do not masquerade as passing functionality. | P1 | Documentation | All | No | Pass |  | Fresh local backend/frontend gates passed; GitHub v4 verification and Vercel deployment succeeded. | Codex SQA | 2026-08-04 | Not Required
[x] | REL-010 | Current | Automated Quality & Release | Release gate formula reviewed | Application dependencies are installed and the target environment is available. | Complete checklist statuses and inspect Release Dashboard. | Dashboard blocks release for failed/blocked Release Gate rows and incomplete current checks. | Release Gate | Process | Excel | Partial | Pass |  | Fresh local backend/frontend gates passed; GitHub v4 verification and Vercel deployment succeeded. | Codex SQA | 2026-08-04 | Not Required
[ ] | REL-011 | Current | Automated Quality & Release | Defects linked and retested | Application dependencies are installed and the target environment is available. | For every Fail, enter defect ID; after fix, fill retest fields and evidence. | No failed row lacks traceability; closed defects have passing retest evidence. | Release Gate | Process | All | No | Not Run |  |  |  |  | Not Required
[ ] | REL-012 | Current | Automated Quality & Release | Formal release sign-off | Application dependencies are installed and the target environment is available. | Complete SQA, developer, instructor, security, and product sign-off as applicable. | Required approvers record decision, name, and date before release. | Release Gate | Process | All | No | Not Run |  |  |  |  | Not Required
[x] | AUTH-001 | Current | Authentication & Account Management | Default student login | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Sign in with student / student. | Login succeeds, a student session is issued, and the assignment catalog loads. | Release Gate | Integration | Web/Backend | Partial | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required | Prototype credential only; replace or deactivate before a real study.
[x] | AUTH-002 | Current | Authentication & Account Management | Default instructor login | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Sign in with instructor / instructor. | Login succeeds, an instructor session is issued, and instructor controls are available. | Release Gate | Integration | Web/Backend | Partial | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required | Prototype credential only; replace before deployment.
[x] | AUTH-003 | Current | Authentication & Account Management | Invalid login and throttling | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Submit an incorrect password five times, then submit another login within 15 minutes. | Invalid attempts return a generic HTTP 401; the additional attempt is throttled with HTTP 429. | Release Gate | Security | Backend | Yes | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required
[x] | AUTH-004 | Current | Authentication & Account Management | Session restoration | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Log in, reload the Flutter app, and call GET /auth/me with the stored Bearer token. | The same active user is restored without asking for credentials again. | P1 | State | Web/Backend | Yes | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required
[x] | AUTH-005 | Current | Authentication & Account Management | Logout revokes the current session | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Log in, call POST /auth/logout, then reuse the same token. | Logout succeeds and subsequent authenticated requests with that token return HTTP 401. | Release Gate | Security | Backend/UI | Yes | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required
[x] | AUTH-006 | Current | Authentication & Account Management | Expired session rejected | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Create an expired session record and call an authenticated endpoint. | The expired token is rejected with HTTP 401 and grants no role access. | Release Gate | Security | Backend | Yes | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required
[x] | AUTH-007 | Current | Authentication & Account Management | Passwords stored only as Argon2 hashes | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Create an account and inspect its database record and JSON import file after synchronization. | The database contains an Argon2 password hash; no reusable plaintext password remains in tracked or runtime account files. | Release Gate | Security | Backend/Repository | Yes | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required
[x] | AUTH-008 | Current | Authentication & Account Management | Instructor role enforcement | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Call assignment and student administration endpoints with instructor, student, missing, and invalid credentials. | Only the instructor succeeds; student receives HTTP 403 and missing/invalid credentials receive HTTP 401. | Release Gate | Security | Backend | Yes | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required | Legacy X-Admin-Token compatibility must not weaken Bearer role checks.
[x] | AUTH-009 | Current | Authentication & Account Management | Role-aware Flutter navigation | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Compare the assignment catalog while signed in as student and instructor. | Only the instructor sees and can open the instructor studio; both roles can sign out. | Release Gate | UI/Security | Web/Mobile | Yes | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required
[x] | AUTH-010 | Current | Authentication & Account Management | Authenticated submission identity cannot be spoofed | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Submit code as a signed-in student while sending a different student_id in the request body. | The stored submission uses the authenticated login ID and ignores the spoofed body value. | Release Gate | Security/Data | Backend | Yes | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required
[x] | AUTH-011 | Current | Authentication & Account Management | Instructor lists student accounts | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Open Student Accounts and call GET /admin/students. | Student accounts load with login ID, participant code, email, active state, and no password/hash data. | P1 | Integration | Web/Backend | Partial | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required
[x] | AUTH-012 | Current | Authentication & Account Management | Create student with generated credential | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Create a student without entering a temporary password. | A secure temporary password is generated and shown exactly once; the account can log in. | Release Gate | Functional | Web/Backend | Yes | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required
[x] | AUTH-013 | Current | Authentication & Account Management | Create student with instructor credential | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Create a student using an instructor-entered password of at least eight characters. | The account is created, the password is hashed, and duplicate login IDs are rejected. | P1 | Functional | Web/Backend | Yes | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required
[ ] | AUTH-014 | Current | Authentication & Account Management | Edit student metadata | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Change a student email and participant code, save, and reload the list. | Normalized values persist and duplicate/invalid email addresses are rejected. | P1 | Data Integrity | Web/Backend | Partial | Not Run |  |  |  |  | Not Required
[x] | AUTH-015 | Current | Authentication & Account Management | Reset student temporary password | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Log in as a student; reset the password as instructor; reuse the old session and password; then use the new password. | Old sessions and password are rejected; the new temporary password works and is shown once. | Release Gate | Security | Backend/UI | Yes | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required
[x] | AUTH-016 | Current | Authentication & Account Management | Deactivate and reactivate student | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Deactivate an active student, attempt login, reactivate, and inspect prior submissions. | Deactivation revokes sessions and blocks login; reactivation restores access without deleting study records. | Release Gate | Lifecycle | Web/Backend | Yes | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required | Prefer deactivation over deletion.
[x] | AUTH-017 | Current | Authentication & Account Management | Manual JSON account synchronization | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Import study_accounts.json with create, update, password, role, and active changes; inspect the file and report. | Valid changes synchronize, absent rows do not delete users, active=false deactivates, errors are reported, and temporary_password is cleared. | Release Gate | Data Integrity | Backend/Repository | Yes | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required | The ignored database remains the login source of truth.
[x] | AUTH-018 | Current | Authentication & Account Management | Last active instructor protection | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Use JSON synchronization to deactivate or demote the only active instructor. | The operation is rejected and at least one active instructor remains. | Release Gate | Security | Backend | Yes | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required
[x] | AUTH-019 | Current | Authentication & Account Management | Forgot-password privacy response | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Request password reset for an existing email, unknown email, and login ID. | All requests return the same generic response; only a matching active account creates a reset message. | Release Gate | Security | Backend/UI | Yes | N/A |  | Intentionally disabled or unnecessary for the controlled v4 professor demo. | Codex SQA | 2026-08-04 | Not Required | Preserved for a future broader study release where applicable.
[x] | AUTH-020 | Current | Authentication & Account Management | One-time password reset token | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Use a reset link, reuse it, try an expired token, and test sessions issued before the reset. | The first valid reset succeeds; reused/expired tokens fail; all previous sessions are revoked. | Release Gate | Security | Backend/UI | Yes | N/A |  | Intentionally disabled or unnecessary for the controlled v4 professor demo. | Codex SQA | 2026-08-04 | Not Required | Preserved for a future broader study release where applicable.
[x] | AUTH-021 | Current | Authentication & Account Management | Real SMTP status and delivery | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Verify unconfigured status, configure provider SMTP values in backend/.env, restart, send a test email, and test invitation/reset delivery. | Missing SMTP blocks email actions without claiming delivery; configured status exposes no secret; the controlled recipient receives the real one-time-link/test email. | Release Gate | Integration | Web/Backend/Email | Partial | N/A |  | Intentionally disabled or unnecessary for the controlled v4 professor demo. | Codex SQA | 2026-08-04 | Not Required | Preserved for a future broader study release where applicable.
[x] | AUTH-022 | Current | Authentication & Account Management | Authentication audit events | Backend is running with a fresh test database; demo accounts are enabled unless the check states otherwise. | Perform login, logout, account create/update/reset, JSON import, and test-email actions; inspect audit_events. | Each security-relevant action records actor, action, resource, timestamp, and non-secret details. | P1 | Security | Backend | Yes | Pass |  | Authentication tests passed; live invalid/student/instructor/session/logout/admin checks passed. | Codex SQA | 2026-08-04 | Not Required
[ ] | FUT-002 | Future | Future Roadmap Readiness | Courses, enrollments, and ownership | Application dependencies are installed and the target environment is available. | Create courses, enroll users, assign instructors, and verify isolation. | Course data and assignments are visible only to authorized membership. | P1 | Future Functional | All | No | Deferred |  |  |  |  | Not Required
[ ] | FUT-003 | Future | Future Roadmap Readiness | Assignment version history and rollback | Application dependencies are installed and the target environment is available. | Publish several versions; inspect history; roll back by creating a new published version. | History remains immutable and student submissions retain original version. | P1 | Future Versioning | Backend/UI | No | Deferred |  |  |  |  | Not Required
[ ] | FUT-004 | Future | Future Roadmap Readiness | Object storage integration | Application dependencies are installed and the target environment is available. | Upload/download starter packages, assets, hidden tests, and simulation files. | Authorized assets are durable, versioned, and unavailable to unauthorized clients. | P0 | Future Integration | Backend | No | Deferred |  |  |  |  | Not Required
[ ] | FUT-005 | Future | Future Roadmap Readiness | Background grading jobs | Application dependencies are installed and the target environment is available. | Submit long-running task; poll, cancel, retry, and recover worker failure. | Job lifecycle is durable, idempotent, observable, and bounded. | P0 | Future Resilience | Backend/UI | No | Deferred |  |  |  |  | Not Required
[ ] | FUT-006 | Future | Future Roadmap Readiness | Common simulation adapter | Application dependencies are installed and the target environment is available. | Run code-only and simulation assignments through common workflow. | Both return the same high-level submission/evidence contract. | P0 | Future Architecture | All | No | Deferred |  |  |  |  | Not Required
[ ] | FUT-007 | Future | Future Roadmap Readiness | Deterministic simulation repeatability | Application dependencies are installed and the target environment is available. | Run same assignment/configuration/seed multiple times. | Metrics and grader result are reproducible within documented tolerance. | P0 | Future Simulation | Worker | No | Deferred |  |  |  |  | Not Required
[ ] | FUT-008 | Future | Future Roadmap Readiness | Simulation artifacts and replay | Application dependencies are installed and the target environment is available. | Complete simulation and open replay/screenshots/logs. | Artifacts belong to the correct attempt/version and are access-controlled. | P1 | Future Simulation | All | No | Deferred |  |  |  |  | Not Required
[ ] | FUT-009 | Future | Future Roadmap Readiness | AI tutor evaluation suite | Application dependencies are installed and the target environment is available. | Run curated success, misconception, prompt-injection, privacy, and solution-leak cases. | Quality/safety thresholds pass before enabling AI broadly. | P0 | Future AI Safety | Backend | No | Deferred |  |  |  |  | Not Required
[ ] | FUT-010 | Future | Future Roadmap Readiness | AI cost and rate controls | Application dependencies are installed and the target environment is available. | Exercise per-user/course budgets, concurrency, rate limits, and fallback. | Costs and latency are bounded; learning workflow remains available. | P0 | Future AI Operations | Backend | No | Deferred |  |  |  |  | Not Required
[ ] | FUT-011 | Future | Future Roadmap Readiness | Instructor analytics | Application dependencies are installed and the target environment is available. | Generate attempts, scores, misconceptions, hints, and completion events. | Dashboard metrics reconcile with underlying records and respect privacy. | P1 | Future Analytics | All | No | Deferred |  |  |  |  | Not Required
[ ] | FUT-012 | Future | Future Roadmap Readiness | LMS/gradebook integration | Application dependencies are installed and the target environment is available. | Sync roster/assignment/grade using test LMS. | Mappings are correct, idempotent, secure, and auditable. | P2 | Future Integration | All | No | Deferred |  |  |  |  | Not Required
[ ] | FUT-013 | Future | Future Roadmap Readiness | Accessibility conformance audit | Application dependencies are installed and the target environment is available. | Run automated and manual WCAG audit across web/mobile critical paths. | Target conformance is met with documented exceptions and remediation. | P1 | Future Accessibility | All | No | Deferred |  |  |  |  | Not Required

## Assignment Matrix
Checked? | Assignment ID | Stable ID | Version | Title | Published | Detail Loads | Starter Compiles | Starter Executes | Official Solution | Public Run | Hidden Grading | Evidence UI | Solution Protection | Hint Policy | Simulation Config | Last Verified | Evidence | Notes
[x] | 1 | robotics-assignment-1 | 3 | Obstacle Avoidance: Bug Algorithm Scenario 1 | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | 2026-08-04 | 76 backend tests; all official solutions; 32 Flutter tests; live API/browser smoke. | Verify consistent Euclidean/boundary distance and no embedded solution.
[x] | 2 | robotics-assignment-2 | 2 | Obstacle Avoidance: Bug Algorithm Scenario 2 | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | 2026-08-04 | 76 backend tests; all official solutions; 32 Flutter tests; live API/browser smoke. | Verify four expected calculation variables and total path length.
[x] | 3 | robotics-assignment-3 | 3 | Autonomous Robot Navigation in a Dynamic Office Environment | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | 2026-08-04 | 76 backend tests; all official solutions; 32 Flutter tests; live API/browser smoke. | Verify movable obstacle activates the configured half-circle detour.
[x] | 4 | robotics-assignment-4 | 2 | Calculating Safe Trajectory using Vector Field Histogram (VFH) | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | 2026-08-04 | 76 backend tests; all official solutions; 32 Flutter tests; live API/browser smoke. | Verify histogram and optimal-sector calculations.

## Defect Log
Defect ID | Title | Severity | Category | Environment | Steps to Reproduce | Expected | Actual | Status | Owner | Found Date | Fix Version / Commit | Retest Result | Retest Date | Evidence Link / Path | Notes
Enter the first real v4 defect here. No new product defect was found in the 2026-08-04 SQA run.

## Release Sign-off
Release Sign-off
Sign only after the Release Dashboard is complete, all Release Gate checks are resolved, and defects have retest evidence.
Gate | Required Evidence | Status | Owner | Date | Comments
Automated backend tests | pytest output | Pass | Codex SQA | 2026-08-04 | 76 pytest checks passed; pip check and compileall passed.
Flutter analysis/tests/build | Command output | Pass | Codex SQA | 2026-08-04 | Analyzer clean; 33 tests passed; release web build passed.
All published assignments validate | Validation report | Pass | Codex SQA | 2026-08-04 | Four published versioned assignments passed repository/grader validation.
All official solutions pass | Per-assignment evidence | Pass | Codex SQA | 2026-08-04 | Assignments 1-4 official solutions passed modular graders.
Desktop/mobile critical path | Screenshots or test record | Partial | Codex SQA | 2026-08-04 | Live Chrome desktop passed; responsive widget tests passed; independent device/accessibility audit remains.
Sandbox security checks | Timeout/import/output/resource evidence | Partial | Codex SQA | 2026-08-04 | Dedicated authenticated sandbox service passes local automated and two-process checks; Render image build and live penetration/resource evidence remain open.
Instructor workflow | Create/edit/validate/publish evidence | Partial | Codex SQA | 2026-08-04 | Live studio/accounts read paths passed; mutation paths passed automated tests but were not executed against production data.
Authentication and account management | Login, role, session, password, account, audit, and email evidence | Pass | Codex SQA | 2026-08-04 | Student/instructor/invalid/session/logout/role/admin checks passed; self-service email reset is out of scope.
Secrets and source diff review | Git evidence | Pass | Codex SQA | 2026-08-04 | No tracked environments or real credentials; one synthetic migration-test URL matched the scanner.
Defect retest complete | Defect IDs and retest evidence | N/A | Codex SQA | 2026-08-04 | No new product defect was found in this SQA cycle.
Approvals
Role | Name | Decision | Date | Signature / Evidence | Comments
SQA Lead |  | Pending
Development Lead |  | Pending
Instructor / Curriculum Owner |  | Pending
Security / Platform Reviewer |  | Pending
Product / Research Lead |  | Pending

## Runbook
SQA Execution Runbook
Run commands from the repository root unless a different working directory is shown. Never put API keys or instructor tokens into the workbook.
Section | Purpose | Command / Procedure | Expected Result
Install | Create Python environment | python -m venv venv | venv directory is created
Install | Install backend packages | .\venv\Scripts\python.exe -m pip install -r .\backend\requirements.txt | Installation succeeds
Install | Install Flutter packages | Set-Location .\frontend; flutter pub get; Set-Location .. | Dependency resolution succeeds
Run | Start backend (Terminal 1) | .\venv\Scripts\python.exe .\backend\run.py | Backend remains running at http://127.0.0.1:5000
Run | Start frontend (Terminal 2) | Set-Location .\frontend; flutter run -d chrome --dart-define=API_BASE_URL=http://127.0.0.1:5000 | Chrome opens the catalog
Backend QA | Run backend tests | Set-Location .\backend; ..\venv\Scripts\python.exe -m pytest -q | All maintained tests pass
Backend QA | Check package integrity | Set-Location .\backend; ..\venv\Scripts\python.exe -m pip check | No broken requirements
Backend QA | Compile Python modules | Set-Location .\backend; ..\venv\Scripts\python.exe -m compileall -q . | No compilation errors
Frontend QA | Static analysis | Set-Location .\frontend; flutter analyze | No issues found
Frontend QA | Widget/state tests | Set-Location .\frontend; flutter test | All tests pass
Frontend QA | Release web build | Set-Location .\frontend; flutter build web --dart-define=API_BASE_URL=http://127.0.0.1:5000 | Build succeeds in .flutter_build\web
Docker QA | Validate Compose | docker compose config | Configuration resolves
Docker QA | Build sandbox image | docker compose --profile build build sandbox-image | Image builds
Docker QA | Start production-like services | docker compose up --build postgres redis backend | Services become healthy
Git QA | Check maintained source whitespace | git diff --check -- . ':!env' ':!venv' | No maintained-source errors
Git QA | Review source changes | git status --short | Only intended source/docs/artifacts appear
Evidence | Record pass | Set Status=Pass, Checked?=[x], enter tester/date, and attach command output/screenshot/path. | Row is auditable
Evidence | Record failure | Set Status=Fail, create Defect Log row, add Defect ID and actual evidence. | Failure is traceable
Evidence | Record blocked test | Set Status=Blocked and document exact external/environment blocker. | Limitation is explicit
Retest | Verify a fix | Repeat original steps, update Retest Status/date/evidence, and close the linked defect only after success. | Fix is proven
Auth QA | Run authentication and account tests | Set-Location .\backend; ..\venv\Scripts\python.exe -m pytest tests\test_auth.py -q | All focused authentication tests pass
Auth API | Verify current port-5000 backend | Open http://127.0.0.1:5000/docs; verify /health, /auth/login, /auth/me, /admin/students, and /admin/email/status. | Current FastAPI routes respond and role protection is enforced
Account JSON | Verify manual cohort synchronization | Edit ignored backend\data\study_accounts.json; sign in as instructor; Student Accounts > Import study_accounts.json; inspect the report. | Valid changes synchronize and temporary passwords are cleared
Email QA | Verify real SMTP delivery | Add provider SMTP values to ignored backend\.env; restart backend; Student Accounts > Send test; use a controlled recipient. | Status shows configured and the real test email arrives
Release | Make decision | Review Release Dashboard and complete Release Sign-off. | No unresolved Release Gate failure or block
V4 Live | Verify live health | Invoke-RestMethod https://robotics-programming-lab-api.onrender.com/health | HTTP 200; status ok; API 4.0.0
V4 Live | Verify login-first entry | Open https://robotics-programming-lab.vercel.app/ in a browser with a prior session | The public root shows login and does not display credentials
V4 Live | Verify authenticated refresh | Sign in, confirm /app, then refresh the page | Session restores on /app; assignment catalog remains visible
V4 Release | Verify hosted CI | Review the latest v4-live GitHub Actions run and Vercel deployment | Backend/frontend CI and production deployment are successful
V4 Sandbox | Create/sync secure grader service | Sync render.yaml; confirm robotics-programming-lab-sandbox uses backend/Dockerfile.sandbox-service and a generated SANDBOX_API_TOKEN. | Sandbox /health returns status ok; no database or OpenAI variables exist on the service.
V4 Sandbox | Connect API to secure grader | Set API SANDBOX_URL to the sandbox public HTTPS URL; confirm SANDBOX_BACKEND=remote and the shared token reference; redeploy API. | API starts successfully; production refuses subprocess or incomplete remote configuration.
V4 Sandbox QA | Verify live execution boundary | Log in as a controlled student; submit one official solution and one import os probe; inspect both service logs without recording code or secrets. | Correct solution passes once; unsafe import fails safely; UI stops; no secret or stack trace is returned.
Staging | Start complete local application | .\scripts\run-local.ps1 | Sandbox, backend, and Flutter become healthy; AI is off by default
Staging | Start on alternate ports when v3 is running | .\scripts\run-local.ps1 -FrontendPort 18080 -BackendPort 15000 -SandboxPort 15001 | The staging instance runs without attaching to the older project
Staging | Stop managed local application | .\scripts\stop-local.ps1 | Only recorded staging process trees stop and their listeners close
Staging QA | Run complete automated gate | .\scripts\verify-local.ps1 | Backend, dependencies, compilation, Flutter analysis/tests, and release build pass
Release QA | Verify clean candidate source | .\scripts\check-release.ps1 | Working tree, generated-file audit, remotes, and candidate SHA pass
Git | Confirm remote separation | git remote -v | origin is staging; production is Robotics-Programming-Lab; IUSE is archive-only
Production | Promote an approved immutable release | .\scripts\promote-release.ps1 -ReleaseTag v4.0.0 -ConfirmProduction | After explicit approval, the exact staging SHA and tag reach production atomically
Severity and Status Definitions
Value | Meaning | Release Effect | Required Action
Critical | Security compromise, data loss, unsafe execution, or platform unavailable | Immediate stop | Fix before any release
High | Critical workflow incorrect or inaccessible with no acceptable workaround | Blocks release | Fix and retest
Medium | Important behavior incorrect with limited workaround | Risk decision required | Plan fix and document
Low | Minor presentation, usability, or documentation issue | Usually does not block | Track and prioritize
Not Run | Test has not been executed | Release incomplete for current scope | Execute or justify N/A
Pass | Actual result matches expected result | Contributes to readiness | Attach evidence
Fail | Actual result does not match expected result | Release Gate failures block | Create defect and fix
Blocked | External/environment condition prevents execution | Release Gate blocks unless explicitly waived | Document blocker and owner
N/A | Test does not apply to this release/environment | Excluded with justification | Explain in Notes
Deferred | Planned future capability not in current release | Excluded from current completion | Review during planning

## Lists (hidden)
Status | Priority | Automation | Check | Retest | Defect Status | Severity | Decision | Scope | Test Type
Not Run | Release Gate | Yes | [ ] | Not Required | Open | Critical | Pending | Current | Automated
Pass | P0 | Partial | [x] | Pass | In Progress | High | Approved | Future | API
Fail | P1 | No |  | Fail | Fixed | Medium | Rejected |  | Integration
Blocked | P2 |  |  | Blocked | Closed | Low | Conditional |  | Manual
N/A |  |  |  | Not Run | Deferred |  |  |  | Security
Deferred | [8 empty] | Accessibility
Performance
Content Review
Process